## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For students
ⓒ2023 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung Innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2024-01-31
Project Team Name | Outliers
Project Topic | SmartMeds (Medical Recommender System)
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 | [6 empty] | W2 | [6 empty] | W3 | [6 empty] | W4 | [6 empty] | W5 | [6 empty] | W6
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43
 | time axis 2023-12-20 to 2024-01-31
1. Data Acquisition | Madhumitha recomended the data, we fitch it UCI machine Learning repo |  | 20/12/2023 | 13/1/2024 | All Members | Code Data Report | Done | bar: 2023-12-20 to 2024-01-13; 2024-01-30 to 2024-01-31
2. Preprocessing of the data | Data reading and EDA +Data Cleaning +Feature Engineering +Natural Language techniques +API Integration |  | 20/12/2024 | 26/1/2024 | Ahmed Madhumitha | Code Data Report | Done
3. Build and train the model | Modeling and Tuning |  | 26/1/2024 | 29/1/2024 | All Members | Code Report | Done | bar: 2024-01-26 to 2024-01-31
4. Evaluate the Performance | We did tuning and evaluating the model in grid_search and Cross validation |  | 27/1/2024 | 30/1/2024 | Ahmed Madhumitha | Code Report | Done | bar: 2024-01-27 to 2024-01-31
5. Finalizing the Final report | Everyone of us helped in a certain way to the final report, by writing the areas they worked in |  | 30/1/2024 | 31/1/2024 | All Members | Report | Done | bar: 2024-01-30 to 2024-01-31
6. Working on the PPT | We worked on the ppt as a team and each on of us had a section to edit |  | 31/1/2024 | 31/1/2024 | Taha, Madhumitha, Ahmed, Ranim | PPT | Done | bar: 2024-01-27 to 2024-01-30
7. Preparing for the demo | We write a script for the final pitch, Ahmed will gonna be the speaker |  | 27/1/2024 | 30/1/2024 | Taha | - | Done
8. Submission of Capstone Final Report, Presentation and Coding Reference | We prepare all the documents to be sent to the Samsung Team |  | 31/1/2024 | 31/1/2024 | Taha | Report Presentation Coding | Done | bar: 2024-01-31
9. Demo |  |  | 27/1/2024 | 2024-10-01 | Ranim | PPT | Done | bar: 2024-01-27 to 2024-01-31
s